## Dev Estimate
DEVELOPMENT ESTIMATE |  |  |  |  | Modules | Engineering Complexity /Features
Role | Pages | Frontend (Days) | Backend (Days) | Total (Days) | Module | Features / Complexity | Notes
Foundation | 20 | 10 | 19 | 29 | Login/Verification
Super Admin
| 3 | 5 | 1 | 6 | Dashboard | Live Data Integration
Chart/Graph based live dashboard
| 16 | 10 | 7 | 17 | Compliance & Audit Center
|  | 5 | 2 |  |  | Chart/Graph based report
|  | 1 | 0 |  |  | Audit Log
|  | 1 | 2 |  |  | Multi-File format report export system
|  | 2 | 2 |  |  | Custom/recurring report generation
|  | 1 | 1 |  |  | Incident Summary
| 20 | 10 | 11 | 21 | Agency Management
|  | 4 | 3 |  |  | Agency CRUD
|  | 1 | 1 |  |  | Agency document management
|  | 1 | 3 |  |  | Bulk upload/ upload agency details through excelsheet)
|  | 1 | 1 |  |  | Activity log
|  | 1 | 1 |  |  | Agency Customers
|  | 1 | 1 |  |  | Agency Agents
|  | 1 | 1 |  |  | Notification management
| 13 | 21 | 29 | 50 | Global Setting
|  | 1 | 2 |  |  | Platform Set-up | Setting licence/registration details and contact information about the platform
|  | 2 | 3 |  |  | Compliance management
|  |  | 1 |  |  | Audit log retention management
|  | 2 | 1 |  |  | Policy Governance | Terms & condition, privacy policy, data policy
|  | 1 | 1 |  |  | Compliance document management
|  | 2 | 4 |  |  | Notification and Alert Management
|  | 1 | 1 |  |  | System Notification Management
|  | 2 | 3 |  |  | Routing and Esclation Management
|  | 2 | 5 |  |  | Platform Security Management | Password Policy, Multi-Factor Authentication (MFA), Session Timeout, Concurrent Session
|  | 5 | 5 |  |  | Integration Management | Enabling/Disabling integrations of 3rd party platofrms like crm, payment providers,sms providers etc
|  | 3 | 3 |  |  | other notification unit mangement
| 10 | 3 | 3 | 6 | Role Management
|  | 2 | 2 |  |  | Role CURD
|  | 1 | 1 |  |  | Assigning members to role
| 10 | 6 | 5 | 11 | Staff Management
|  | 4 | 2 |  |  | Staff Crud
|  | 2 | 3 |  |  | Staff Activity Log with export option
Security Admin
| 3 | 3 | 3 | 6 | Dashboard
|  | 1 | 1 |  |  | Users security activity logs
|  | 1 | 1 |  |  | Active Threats log
|  | 1 | 1 |  |  | Live active notification
| 12 | 10 | 9 | 19 | Incident Management
|  | 3 | 2 |  |  | Multlevel filter based Incident listing
|  | 4 | 5 |  |  | Multi-File format report export system
|  | 1 | 1 |  |  | Insident Assignment system
|  | 2 | 1 |  |  | Insident Detail view
| 10 | 3 | 3 | 6 | Access Log System
|  | 1 | 1 |  |  | Category based user log listing
|  | 2 | 2 |  |  | Log Export in excel/pdf
| 5 | 7 | 8 | 15 | Admin Security center
|  | 3 | 3 |  |  | IP Whitelist management
|  | 2 | 2 |  |  | Profile Setup
|  | 2 | 3 |  |  | Platform Security Management
|  | 2 | 2 |  | Security Help Hub
Security Knowledge Base
Agency
| 19 | 8 | 15 | 23 | Account Creation
|  | 3 | 6 |  |  | MFA with email and phone number | MFA-Multi Factor Authentication
|  | 4 | 6 |  |  | Agency Setup | 4 set details. 1) Agency Details including logo 2) Admin & Contact details 3) Business profile details 4) Package(subscription) selection
|  | 1 | 3 |  |  | Bulk upload/ upload agency details through excelsheet)
| 4 | 3 | 4 | 7 | Agency KYC
|  | 2 | 3 |  |  | Document Submition | 8 different document need to be submited (pdf,jpg,png)
|  | 1 | 1 |  |  | Document Verification | Manual verification from admin
| 4 | 2 | 2 | 4 | Dashboard
| 14 | 8 | 8 | 16 | Agent Manaegment |  | Agent will handle direct customers
|  | 3 | 2 |  |  | Agent CRUD
|  | 1 | 1 |  |  | B2B Segment/B2C segment | Agent will handle other companies/agency
|  | 3 | 2 |  |  | Agent activation status Management | In this the agent can be suspended, deactivated,reactivated, moved to inactivestate
|  | 1 | 3 |  |  | Bulk upload/ upload agent details through excelsheet)
| 12 | 8 | 6 | 14 | Help&Support
|  | 2 | 1 |  |  | Search for FAQ & Articles
|  | 1 | 1 |  |  | FAQ with categorization
|  | 2 | 2 |  |  | Article listing with details
|  | 3 | 2 |  |  | Issue reporting/Ticketing system
| 26 | 10 | 11 | 21 | Collection Hub
|  | 5 | 5 |  |  | Task Management
|  | 1 | 1 |  |  | Esclation Management
|  | 1 | 1 |  |  | Broken PTP management
|  | 1 | 1 |  |  | Dispute Queue management
|  | 2 | 3 |  |  | Task Automation management
| 10 | 9 | 9 | 18 | Customer Management
|  | 4 | 3 |  |  | B2C Customer with loan (CRUD)
|  | 4 | 3 |  |  | Customer Loan Management
|  | 1 | 3 |  |  | Bulk upload customers
| 6 | 7 | 9 | 16 | Agency Settings
|  | 3 | 2 |  |  | Agency Details Management
|  | 1 | 2 |  |  | Compliance/Docuement Management
|  | 2 | 2 |  |  | Communication Template management
|  | 1 | 1 |  |  | Business Hours Management
2
| 8 | 6 | 7 | 13 | Report and Inshights
|  | 3 | 3 |  |  | Custome Reports
|  | 3 | 4 |  |  | Pre-Defined Reports
Agent
| 6 | 4 | 4 | 8 | Dashboard
|  | 1 | 1 |  |  | My Taks
|  | 1 | 1 |  |  | Esclation list
|  | 2 | 2 |  |  | Customer Interation
| 1 | 2 | 2 | 4 | Performance Dashboard
|  | 2 | 2 |  |  | Show performance of the agent through different graph
| 6 | 5 | 3 | 8 | Customer Assignment/Management
|  | 2 | 2 |  |  | Customer Listing with assignment
|  | 3 | 1 |  |  | Customer Detail view
| 6 | 5 | 5 | 10 | Task Management
|  | 2 | 2 |  |  | Overview
|  | 2 | 2 |  |  | Interactions
|  | 1 | 1 |  |  | Activity Log
| 10 | 8 | 8 | 16 | Communication management
|  | 3 | 3 |  |  | Log Communictation | Email/Call/SMS/Letter/Visit
|  | 3 | 3 |  |  | Communication template creation
|  | 2 | 2 |  | Help & Support
Article support
Support Ticket
| 4 | 6 | 6 | 12 | Settings
|  | 3 | 2 |  |  | Profile Settings
|  | 1 | 2 |  |  | Notification settings
|  | 2 | 2 |  |  | Document management
Customer
| 6 | 7 | 7 | 14 | Overview/Dashboard
|  | 4 | 4 |  |  | Make payment
|  | 3 | 3 |  |  | Statement Management
| 8 | 7 | 7 | 14 | Loan Management
|  | 2 | 2 |  |  | Dashboard
|  | 2 | 2 |  |  | Statement management
|  | 1 | 1 |  |  | Payment History
|  | 2 | 2 |  | Help & Support
Article support
Support Ticket
FAQ
| 8 | 7 | 4 | 11 | Settings
|  | 2 | 1 |  |  | Profile Settings
|  | 2 | 1 |  |  | Document management
|  | 3 | 2 |  |  | Secutiry settings
Cross-cutting Concerns
|  | 6 | 3 | 9 | Multilanguage Landing Page
|  | 6 | 12 | 18 | Authentication
|  | 2 | 4 |  |  | Role based user management
|  | 2 | 4 |  |  | 2factor authentication
|  | 2 | 4 |  |  | Strict Role based audit logs
|  | 3 | 6 | 9 | Notification system
|  | 1 | 2 |  |  | Custom managed
|  | 1 | 2 |  |  | Template based
|  | 1 | 2 |  |  | Action Enabled Notification
|  |  | 2 | 2 | Multi language support
|  |  | 1 | 1 | Data Enryption
|  | 2 | 2 | 4 | Architect
|  |  |  | 458 | Total man days excluding testing,buffer, missing support module
|  |  |  | 91.6 | 20% (testing) in man days
|  |  |  | 549.6 | Total man days + testing man days
|  |  |  | 20 | Additional buffer
569.6
Total number of pages | 280 |  |  | 569.6 | Total man days including testing,buffer, missing support module
Things to consider
SAMA Compliances
Audit log
Data encryption

## Resource Plan
RESOURCE PLAN
Munjz - Debt Collection Platform (Saudi / SAMA Regulated)
ASSUMPTIONS
Hours per Day | 8
Working Days/Month | 22
Project Duration (months) | 12
Role | Level | Count | Hourly Rate ($) | Daily Rate (8hrs) | Man-Days | Total Hours | Total Cost ($) | Allocation Notes
Tech Lead / Architect | Senior | 1 | 32 | 256 | 165 | 1320 | 42240 | Full 3mo, half 9mo
Frontend Developer (Sr) | Senior | 1 | 25 | 200 | 109 | 872 | 21800 | Full project
Frontend Developer (Mid) | Mid | 1 | 22 | 176 | 108 | 864 | 19008 | Full project
Backend Developer (Sr) | Senior | 1 | 30 | 240 | 121 | 968 | 29040 | Full project
Backend Developer (Mid) | Mid | 1 | 24 | 192 | 120 | 960 | 23040 | Full project
QA Engineer (Mid) | Mid | 1 | 22 | 176 | 92 | 736 | 16192 | Full project
QA Engineer (Jr) | Junior | 1 | 20 | 160 | 69 | 552 | 11040 | Joins at 25% progress
DevOps Engineer | Mid-Sr | 1 | 24 | 192 | 198 | 1584 | 38016 | Half 6mo, full 6mo
Project Manager | Senior | 1 | 28 | 224 | 70 | 560 | 15680 | Full project
TOTAL |  | 9 |  |  | 1052 | 8416 | 216056
TECH LEAD ALLOCATION DETAIL
Period | Months | Allocation | Days/Month | Total Days
Months 1-3 | 3 | 100% | 22 | 66
Months 4-12 | 9 | 50% | 11 | 99
Total |  |  |  | 165
DEVOPS ALLOCATION DETAIL
Period | Months | Allocation | Days/Month | Total Days
Months 1-6 | 6 | 50% | 11 | 66
Months 7-12 | 6 | 100% | 22 | 132
Total |  |  |  | 198

## Timeline
PROJECT TIMELINE
Team: 2 FE, 2 BE, 2 QA, 1 PM, 1 Tech Lead, 1 DevOps
Phase | Module | FE Days | BE Days | Total Days | Duration (parallel) | Start Week | End Week | Calendar Days | QA Jr | DevOps
Phase 1: Foundation & Core |  | 16 | 32 | 48 | 16 | 1 | 4 | 20 | No | Half
| Login/Verification | 10 | 19 | 29
| Authentication | 6 | 12 | 18
| Data Encryption | 0 | 1 | 1
Phase 2: Super Admin |  | 55 | 56 | 111 | 28 | 5 | 10 | 30 | Yes | Half
| Dashboard | 5 | 1 | 6
| Compliance & Audit Center | 10 | 7 | 17
| Agency Management | 10 | 11 | 21
| Global Setting | 21 | 29 | 50
| Role Management | 3 | 3 | 6
| Staff Management | 6 | 5 | 11
Phase 3: Security Admin |  | 23 | 23 | 46 | 12 | 11 | 13 | 15 | Yes | Half
| Dashboard | 3 | 3 | 6
| Incident Management | 10 | 9 | 19
| Access Log System | 3 | 3 | 6
| Admin Security Center | 7 | 8 | 15
Phase 4: Agency Portal |  | 61 | 71 | 132 | 36 | 14 | 21 | 40 | Yes | Half
| Account Creation | 8 | 15 | 23
| Agency KYC | 3 | 4 | 7
| Dashboard | 2 | 2 | 4
| Agent Management | 8 | 8 | 16
| Help & Support | 8 | 6 | 14
| Collection Hub | 10 | 11 | 21
| Customer Management | 9 | 9 | 18
| Agency Settings | 7 | 9 | 16
| Reports & Insights | 6 | 7 | 13
Phase 5: Agent Portal |  | 30 | 28 | 58 | 15 | 22 | 24 | 15 | Yes | Half
| Dashboard | 4 | 4 | 8
| Performance Dashboard | 2 | 2 | 4
| Customer Assignment/Mgmt | 5 | 3 | 8
| Task Management | 5 | 5 | 10
| Communication Management | 8 | 8 | 16
| Settings | 6 | 6 | 12
Phase 6: Customer Portal |  | 21 | 18 | 39 | 11 | 25 | 27 | 15 | Yes | Half
| Overview/Dashboard | 7 | 7 | 14
| Loan Management | 7 | 7 | 14
| Settings | 7 | 4 | 11
Phase 7: Cross-cutting & Polish |  | 11 | 13 | 24 | 7 | 28 | 29 | 10 | Yes | Full
| Multilanguage Landing Page | 6 | 3 | 9
| Notification System | 3 | 6 | 9
| Multi Language Support | 0 | 2 | 2
| Architect | 2 | 2 | 4
Phase 8: QA & Testing | Full regression & pen testing |  |  | 92 | 92 | 30 | 48 | 95 | Yes | Full
Phase 9: Buffer & Stabilization | Bug fixes & stabilization |  |  | 20 | 20 | 49 | 52 | 20 | Yes | Full
PROJECT SUMMARY | [5 empty] | 1 | 52 | 260
Total: ~52 weeks (~12.1 months) including buffer
QA Jr joins ~25% progress (after Phase 2) ¦ DevOps goes full-time from month 7

## Project Pricing
PROJECT PRICING
Munjz - Debt Collection Platform
ASSUMPTIONS
Working Hours/Day | 8
Working Days/Month | 22
Project Duration | 12 months
RESOURCE COST BREAKDOWN
Resource | Level | Hourly Rate ($) | Man-Days | Total Hours | Total Cost ($) | Notes
Tech Lead / Architect | Senior | 32 | 165 | 1320 | 42240 | Full 3mo, half 9mo
Frontend Developer (Sr) | Senior | 25 | 109 | 872 | 21800 | Full project
Frontend Developer (Mid) | Mid | 22 | 108 | 864 | 19008 | Full project
Backend Developer (Sr) | Senior | 30 | 121 | 968 | 29040 | Full project
Backend Developer (Mid) | Mid | 24 | 120 | 960 | 23040 | Full project
QA Engineer (Mid) | Mid | 22 | 92 | 736 | 16192 | Full project
QA Engineer (Jr) | Junior | 20 | 69 | 552 | 11040 | Joins at 25% progress
DevOps Engineer | Mid-Sr | 28 | 198 | 1584 | 44352 | Half 6mo, full 6mo
Project Manager | Senior | 24 | 70 | 560 | 13440 | Full project
TOTAL |  |  | 1052 | 8416 | 220152
KEY METRICS
Blended Hourly Rate | 26.1587
Average Monthly Investment | 18346
Total Project Investment | 220152

## Project Summary
PROJECT SUMMARY
Munjz - Debt Collection Platform
PROJECT OVERVIEW
Project | Munjz - Debt Collection Platform
Domain | FinTech / SAMA Regulated (Saudi Arabia)
Team Size | 9 resources (2 FE, 2 BE, 2 QA, 1 PM, 1 Tech Lead, 1 DevOps)
Duration | ~52 weeks (~12 months) including buffer
Rate Range | $20 - $32 / hour
EFFORT BREAKDOWN
Category | Man-Days | Man-Hours
Tech Lead / Architect | 165 | 1320
Frontend Development | 217 | 1736
Backend Development | 241 | 1928
QA (Mid - full project) | 92 | 736
QA (Junior - from 25%) | 69 | 552
DevOps Engineer | 198 | 1584
Project Management | 70 | 560
Buffer | 20 | 160
TOTAL | 1072 | 8576
INVESTMENT SUMMARY
Metric | Value
Total Project Investment | 220152
Blended Hourly Rate | 26.1587
Avg Monthly Investment | 18346
Total Man-Days | 1072
Total Man-Hours | 8576
Project Duration | 52 weeks (~12 months)
Team Size | 9 resources (peak)